## Slide 1: SFU Remote Monitoring IT system enhancement
Project initiation document (PID)
July 2019
[Insert Trust Name]

## Slide 2: Purpose of document
This Project Initiation Document should be read in conjunction with the Statement of Work and Memorandum of Understanding which were provided to the Trust on 20th February 2019. In completing it, the Trust will:
Demonstrate their commitment to achieving outcomes mandated in the National Planning Guidance for 2019/2020
Clarify the particular scope of work the Trust will undertake to maximise their benefit from this funding.
Identify their approach to the project, the major risks and their mitigation.
Identify their timescales, agree them with NCEL Cancer Alliance and ring-fence the Trust resources necessary to complete the project and deliver the associated benefits in the agreed time.
The Trust should read through this document, complete sections >>>>>>>> it as shown in the in-line guidance and return to NCEL Caner Alliance 31st August 2019.
Contact details:
Sarita.yaganti1@nhs.net

## Slide 3: PID Approval
The project described in this PID has been incorporated into the Trust programme of work, has been assigned the necessary resources and has been approved to proceed by Trust officers as required by the standing operating instructions of the Trust.

## Slide 4: Key roles and responsibilities
Role | Name | Job title | E-mail | Key responsibilities
NCEL Cancer Alliance Roles |  |  |  | 
Project Lead / Sponsor | Naser Turabi | Programme Director NCEL Cancer Alliance | Naser.turabi@nhs.net | Oversight of the project on behalf of NCEL Cancer Alliance
Workstream Project Manager | Sarita Yaganti | Stratified Follow up Lead | Sarita.yaganti1@nhs.net | Review and approval of the PIDs returned by the Trusts. Coordination between the participating Trusts, to help share best practice. Receive reports of progress from the Trusts. Receive End of Project Review report from Trust project lead NCEL contact for Trust project managers.
Clinical Model Programme Lead |  | Senior Programme Lead – Personalised Care and Cancer |  | 
Trust Roles |  |  |  | 
Project Lead |  |  |  | Oversee the completion of the PID. Return it to NCEL Cancer Alliance Provide IT leadership for the Trust project, manage it, including system installation, configuration and test and associated reporting within the Trust and to NCEL Cancer Alliance. Chair the Trust End of Project Review and submit report to RM Partners
Cancer/ Operational Manager |  |  |  | Identify users, ensure they have accounts and appropriate access rights on the system and ensure that they are appropriately trained. Contribute to testing. Take long term ownership of the system
Breast MDT Clinical Representative |  |  |  | Advise Trust Project Lead on use cases for MDT. Identify MDT users and ensure they are appropriately trained. Contributes to testing.

## Slide 5: Project Background
Stratified Follow Up Remote Monitoring IT system enhancement | 
Goal | National Planning Guidance for 2017/19 states that all Trusts must demonstrate: Progress towards the 2020/21 ambition for all breast cancer patients to move to a stratified follow-up pathway after treatment. A system for remote monitoring by the end of March 2019 Any Trust stratifying patients onto the supported self management pathway will need an enabling IT system. IT systems currently in use in North Central and East London range in reliability and clinical safety from, for example, spreadsheets and paper to a high availability database application with full data and desktop integration with the Trust’s principal clinical system. Functionality also varies greatly. This project is to enhance the functionality, reliability and clinical safety of the Trust’s chosen system in accordance with the Statement of Work (See Appendix A) set out by NCEL Cancer Alliance and thereby qualify for funding and support offered by the Alliance.
Summary | To support implementation of stratified follow up at Trust level, and recognising the essential need for a robust lT solution, NCEL Cancer Alliance, SEL Cancer Alliance and RM Partners were successful in a pan-London bid to NHSE for Transformation Funding. One initiative within the pan-London bid is dedicated funding for Trusts to purchase an IT solution - or configure existing IT systems - to remotely monitor breast, urology and colorectal patients who are directed onto a supported self-management pathway. The financial package of support is a sum of £19,571 per Trust. It is anticipated that this will cover individual trust’s costs incurred in delivering this solution. Receipt of this funding is subject to the necessary conditions being met. The conditions are that the IT must meet the functionality requirements as outlined in the “IT Remote Monitoring System for Stratified Follow-up: Functionality requirements and options appraisal” document outlined in from Slide 7. The project should consist of the following: The Trust will choose the system it intends to enhance – probably the one already installed - its approach to the enhancement project and complete a gap analysis, showing which of the Statement of Work requirements are currently met and which it expects to be met by the end of the project. The Trust will decide the scope of the project, which may include software installation, configuration and test. It may also include integration with existing Trust systems, such as the principal clinical system, radiology system (RIS,) laboratory system (LIMS) and outpatients appointments system. We expect it to include training of users and a system administrator. It could also include an enhancement of the provision for Disaster Recovery or backup. We expect the Trust to take a pragmatic approach to data migration: The funding available from NCEL Cancer Alliance is seen as a contribution to the cost of a mandated project, rather than complete funding, so for most Trusts, we would not expect it to cover the cost of all the enhancements and data migration. The Trust will manage the project in accordance with its own standing instructions, custom and practice, but will also report progress periodically to NCEL Cancer Alliance. The Alliance will facilitate sharing of learning and best practices between Trusts and will also coordinate Trust plans to avoid overloading the main system suppliers. At the end of the project the Trust will hold a review to identify lessons learned, update the gap analysis, enumerate the early benefits to the Trust and submit the report to NCEL Caner Alliance.

## Slide 6: How to complete this PID
The Trust should take about 2 pages to complete this section in order to show:
System Which system they have chosen to enhance in this project and whether it is a standalone system or a module of an existing system at the trust.
Enhancements The gap analysis gives detail of the enhancements expected. This section should overview the enhancements deemed most important by the Trust, for example: Which integration (if any) will be put in place? What are the key functional enhancements sought by the Trust? If navigation between systems will still be required, will the systems be linked to preserve patient context?
Intended outcomes Operational outcomes expected, such as quicker or safer management of patients stratified for supported self management follow up.
Project approach A narrative setting out the main tasks and any sensitivities around them in the context of the Trust, e.g response to particular features of the computing, clinical or operational environment.
Governance An overview of the Trust governance processes for this project.
Any other project features of particular importance to the Trust

## Slide 7: The required functionality of IT systems to ensure that remote monitoring can effectively take place. The system needs to house sufficient information to enable the clinician to manage the patient without the need to access case notes. It is recommended that all functions are delivered. However, if a phased approach to introduction utilise, phase 1 must include the essential components as outlined below.
Functionality Required | Essential | Current System compliance
The ability to pull patients dataset information from the PAS via the local cancer information system | E | 
The ability to pull diagnostic results from the relevant IT systems | E | 
The ability to report on national and London metrics to monitor the numbers of individuals being stratified onto a self-management pathway | E | 
Storage of key diagnostic and patient history data | E | 
The setting of individual patient ranges/tolerances for specific tests | E | 
The scheduling of tests based on user definable follow-up schedules | E | 
An alert system to identify test results for review, due dates exceeded or test results that have exceeded their tolerances | E | 
Provide a summary treatment page with patient history to include test results shown numerically and/or graphically to record the outcome of any event or test | E | 
Provide standard and ad hoc reporting and a routine monitoring function and be amenable to clinical audit | E | 
NHS and HL7 compliant with secure access | E | 
To use a common file format for all data export and to be able to import the data into local IT systems | E | 
Please √ where your current system meets the functionality required

## Slide 8: Desirable Functionality
Functionality Required | Desirable | Current System compliance
A patient portal to enable individuals to access to their diagnostic results and individualised health information and support | D | 
Hold a range of template letters to enable the communication of surveillance results to patients and GP’s by post or electronically | D | 
Log relevant treatment history during the monitoring period including patient contacts | D | 
The ability to report on national and London metrics to monitor the numbers of individuals being stratified onto a self-management pathway | D | 
The ability to provide ad hoc reporting. | D | 
For clinical users, the ability to define the patient’s follow-up schedule based on clinical requirement and patient’s wellbeing. This should include structured data to set follow-up schedules together with a copy of the treatment summary and/or the HNA stored somewhere on the patients record. | D | 
For clinical users, the ability to select each patient’s required future diagnostic tests, the acceptable output ranges/tolerances and the parameters which trigger a recall | D | 
An alert system to call attention to test results for review, due dates approaching or exceeded and test results that have exceeded their tolerances | D | 
The ability to export all clinical and patient contact data entered in the remote monitoring system into the Trust's principal clinical system if required (e.g. for the user to note any interaction with the patient which may be relevant to their care.) | D | 
Near real time (HL7 or appropriate equivalent) data interface in place to achieve the above data export automatically and eliminate the need for manual data transfer or re keying of data. | D | 
Hold a range of template letters to enable communication of surveillance results to patients and their GPs by post or electronically. Populate the letters with patient specific information automatically. | D | 
A full clinical audit trail for forensic/ other use | D | 

## Slide 9: Disaster recovery
Functionality Required | Essential / Desirable | Current System compliance
Disaster recovery. |  | 
One of the following approaches to disaster recovery (or other approach by agreement) must be followed |  | 
The system and its configuration is backed up and can be restored as part of a disaster recovery. |  | 
A copy of the configured system runs on a server at a separate location, kept up to date with changes to configuration and code and the data back-up would be restored to it as part of a disaster recovery. |  | 
A copy of the system and data is kept up to date in near real time (within 20 seconds) on a server at a separate location. As part of a disaster recovery, it can be brought into use quickly with little or no loss of data. |  | 
The system is implemented as a high availability cluster |  | 
The system stores no significant data on paper or in spreadsheets for new patients |  | 
The Trust stores no significant data on paper or in spreadsheets for patients who were admitted to assisted self management 12 or more months ago and are still followed up. |  | 
Clear written instructions for use of the system |  | 
Users trained in the use of the system |  | 
Detailed test scripts to confirm that the system operates as described in the instructions |  | 
Test results and test report from running the test scripts. |  | 

## Slide 10: Risk
Risk | Risk description | Mitigation | RAG
Trust risks |  |  | 
Audit | Without a mature system in place and integrated with the Trust clinical systems, an audit of Trust IT systems may record a non-compliance with the National Planning Guidance for 2017/19 which requires a system for remote monitoring by the end of March 2019 | SFU Remote Monitoring IT system required by the National Planning Guidance for 2017/19. This will minimise adverse audit findings. | 
Data Quality | Because the system is not fed with data directly by source systems at the Trust, appointments, clinical information and other data have to be hand keyed into the system, which is not only labour intensive but prone to miss keying. When this is discovered before the next interaction between Trust and patient, it leads to unplanned rework and the associated disruption. Discovered after, it leads to delays which are visible to the patient, loss of confidence in the hospital and the associated reputational damage among patients. | The interfaces put in place by this project eliminate mis-keying and the associated: Disruption caused when errors were identified early Reputational damage when they were identified late. | 
Back-Up | If the stored data becomes corrupt , remote monitoring of patients cannot proceed until the data has been restored. This amounts to a temporary loss of service and the subsequent catch up. This affects all remote monitoring patients due for interaction with the Trust during the service loss and its catch up period. This leads to reputational damage among patients. | The test of the data restoration process which forms part of this project provides an opportunity to test the written procedure, eliminate any uncertainties in it and therefore reduce the time required to perform a restore should one ever be needed. This reduces the number of patients who would be affected and the associated reputational damage. | 
Disaster Recovery | A major failure of the hardware or the software platform on which this service rests could take days or weeks to resolve, leading to commercial damage as well as reputational damage to the Trust. | The disaster recovery provision put in place by this project reduces the time taken to re-start the service to patients to a matter of hours, substantially reducing commercial and reputational damage to the Trust. | 

## Slide 11
Risk # | Risk description | Mitigation | RAG
Project risks |  |  | 
Supplier resource availability | Trusts across London are addressing the SFU remote monitoring project simultaneously so the most widely used system suppliers could be overwhelmed, leading to delays. | RMP will maintain contact with the widely used system suppliers and appraise them of progress so that they can plan accordingly. Where it is beneficial, RMP will coordinate Trusts to avoid overwhelming suppliers. | 
Trust resource availability | Competing priorities at the Trust may result in Trust resources not being available in a timely manner, leading to delays. | Trust to ensure Exec, Operational and Clinical buy in for this externally funded project to improve the Trust’s conformance to requirements mandated in the National Planning Guidance for 2017/19 . | 
Technical risk | In addressing this enhancement, the Trust will be undertaking many tasks for the first time, leading to decisions that are less than optimally informed and inadvertent adoption of poorer practices. | NCEL Cancer Alliance will facilitate shared learning and shared best practices across participating Trusts. |